## Steps
1 | Overview per chapter
| 1.1 | Write all names used in chapter
2 | ONE by ONE status check
| 2.1 | Check if R is in old and write ID
| 2.2 | Do the same for Matlab and SAS
| 2.3 | Check if it is in github. Write ID and transfer status
3 | New addings
| 3.1 | if not transfered, transfer to ToDo repository (use R_old_id as new github id)
If there is already R version in MVA-ready, copy this folder and add all new things (code, update metainfo, delete old readme)
- in metainfo: do not change "authors". Change "submitted by" only if you run and check the code. Check for yaml
4 | Double/triple check
| 4.1 | Double check; Check the content github vs book
| 4.2 | Github vs. Slides
yaml check in R
library(yaml)
yaml.load_file("/Users/PetraB/GitHub/MVA-ToDo/QID-1225-MVApcasimu/Metainfo.txt")

## Chapters 1 to 9
Chapter | ID github | Name | R |  | Matlab |  | SAS
|  |  | ID old | transfered | ID old | transfered | ID old | transfered | Review Date | Git (R) vs Book | Git vs. Slides | Matlab Check (coincides with R Codes)
1 | 1486 | MVAboxcity | 1486 | Ready | 490 | ToDo | - | Ready | 2016-11-14 | ok |  | ok
1 | 1485 | MVAboxcar | 1485 | Ready | 1408 | ToDo | - | Ready | 2016-11-14 | ok |  | ok
1 | 1484 | MVAboxbank6 | 1484 | Ready | 543 | ToDo | - | Ready | 2016-11-14 | ok |  | ok
1 | 2428 | MVAboxbank1 | 2428 | Ready | 621 | ToDo | - | - | 2016-11-14 | ok |  | ok
1 | 1489 | MVAhisbank1 | 148900% | Ready | 622 | ToDo | - | Ready | 2016-11-14 | ok |  | ok
1 | 1490 | MVAhisbank2 | 1490 | Ready | 437 | ToDo | - | Ready | 2016-11-14 | ok |  | ok
1 | 1528 | MVAashbank | 1528 | Ready | 623 | ToDo | - | - | 2016-11-14 | OK |  | ok
1 | 1493 | MVAdenbank | 1493 | Ready | 469 | ToDo | - | Ready | 2016-11-14 | ok |  | ok
1 | 1206 | MVAcontbank2 | 1206 | Ready | 1512 | ToDo | - | - | 2016-11-14 | ok |  | new graph
1 | 1700 | MVAcontbank3 | 1700 | Ready | - | - | - | - | 2016-11-14 | esthetic differences: the graph on Github seems a bit tilted
1 | 1530 | MVAscabank56 | 1530 | Ready | 1245 | ToDo | - | Ready | 2016-11-14 | ok |  | ok
1 | 1531 | MVAscabank456 | 1531 | Ready | 502 | ToDo | - | - | 2016-11-14 | OK |  | ok
1 | 1491 | MVAdraftbank4 | 1491 | Ready | 1508 | ToDo | - | - | 2016-11-14 | doesn't match + (typo book) |  | new graph
1 | 1736 | MVAfacebank10 | 1736 | Ready | 625 | ToDo | - | - | 2016-11-14 | ok |  | ok
1 | 1737 | MVAfacebank50 | 1737 | Ready | 340 | ToDo | - | - | 2016-11-14 | ok |  | ok
1 | 2453 | MVAandcur | 2453 | Ready | 1236 | ToDo | - | - | 2016-11-16 | ok |  | ok
1 | 1569 | MVAandcur2 | 1569 | Ready | 364 | ToDo | - | - | 2016-11-16 | ok |  | ok
1 | 1570 | MVAparcoo1 | 1570 | Ready | 626 | ToDo | - | - | 2016-11-16 | ok |  | ok
1 | 1573 | MVApcp2 | 1573 | Ready | 628 | ToDo | - | - | 2016-11-16 | ok |  | ok
1 | 1574 | MVApcp3 | 1574 | Ready | 532 | ToDo | - | - | 2016-11-16 | ok |  | ok
1 | 1575 | MVApcp4 | 1575 | Ready | 629 | ToDo | - | - | 2016-11-16 | ok |  | ok
1 | 1576 | MVApcp5 | 1576 | Ready | 630 | ToDo | - | - | 2016-11-17 | ok |  | ok
1 | 1577 | MVApcp6 | 1577 | Ready | 417 | ToDo | - | Ready | 2016-11-17 | ok |  | ok
1 | 1578 | MVApcp7 | 1578 | Ready | 631 | ToDo | - | - | 2016-11-17 | esthetic differences: labels |  | ok
1 | 1579 | MVApcp8 | 1579 | Ready | 632 | ToDo | - | - | 2016-11-17 | ok |  | ok
1 | 1572 | MVApcp1 | 1572 | Ready | 627 | ToDo | - | - | 2016-11-17 | ok |  | ok
1 | 1196 | MVageIncome | 1196 | Ready | - | - | - | Ready | 2016-10-26 | ok
1 | 1195 | MVAageCom | 1195 | Ready | - | - | - | Ready | 2016-10-26 | it doesn't match: Outlier in Github data (Age=1000)
1 | 1213 | MVAincomeLi | 1213 | Ready | - | - | - | Ready | 2016-10-26 | it doesn't match: Not all data points match
1 | 1611 | MVApcphousing | 1611 | Ready | 470 | ToDo | - | - | 2016-11-22 | ok |  | ok
1 | 1609 | MVAdrafthousing | 1609 | Ready | 633 | ToDo | - | - | 2016-11-22 | it doesn't match |  | ok
1 | 1610 | MVAdrafthousingt | 1610 | Ready | 634 | ToDo | - | - | 2016-11-22 | it doesn't match |  | ok
1 | 2298 | MVAboxbhd | 2298 | Ready | 516 | ToDo | - | Ready | 2016-11-22 | ok |  | ok
1 | 1487 | MVAhexaAl | 1487 | Ready | 1702 | ToDo | - | Ready | 2016-11-22 | it doesn't match: Github shows just one graph out of 4 |  | ok
3 | 1529 | MVAscabank45 | 1529 | Ready | 1244 | ToDo | - | Ready | 2016-11-22 | ok |  | ok
3 | 1620 | MVAscapull1 | 1620 | Ready | 638 | ToDo | - | Ready | 2016-11-22 | ok |  | ok
3 | 1621 | MVAscacar | 1621 | Ready | 370 | ToDo | - | Ready | 2016-11-22 | ok |  | ok
3 | 1622 | MVAscapull2 | 1622 | Ready | 1246 | ToDo | - | Ready | 2016-11-22 | ok |  | ok
3 | 1617 | MVAregpull | 1617 | Ready | 640 | ToDo | - | Ready | 2016-11-22 | ok |  | ok
3 | 1618 | MVAregzoom | 1618 | Ready | 365 | ToDo | - | Ready | 2016-11-22 | ok |  | ok
3 | 1616 | MVAregbank | 1616 | Ready | 524 | ToDo | - | Ready | 2016-11-22 | ok |  | ok
3 | 1612 | MVAcorrnorm | 1612 | ready | 344 | ToDo | - | Ready | 2016-11-22 | it doesn't match: Not all data points match |  | ok
3 | 1614 | MVAdescbh | 1614 | Ready | 509 | ToDo | - | Ready | 2016-11-22 | it doesn't match: table is not included in GitHub |  | ok
3;7 | 1615 | MVAlinregbh | 1615 | Ready | 499 | ToDo | - | Ready | 2016-11-22 | ok |  | ok
4 | 942 | MVAdenbank2 | 942 | Ready | 513 | ToDo |  | Ready | 2016-11-22 | ok |  | ok
4 | 1207 | MVAdenkbank3 | 1207 | Ready | 1630 | ToDo | . | - | 2016-11-22 | ok |  | ok
4 | 1629 | MVAcontnorm | 1629 | Ready | 500 | ToDo | - | - | 2016-11-22 | it doesn't match Not all data points match |  | ok
4 | 1199 | MVAcltbern | 1199 | Ready | 1627 | ToDo | - | - | 2016-11-22 | graphs don't match |  | ok
4 | 1200 | MVAcltbern2 | 1200 | Ready | 1628 | ToDo | - | - | 2016-11-23 | graphs don't match perfectly |  | ok
4 | 1267 | MVAgausscauchy | 1267 | Ready | 1681 | ToDo | - | - | 2016-11-23 | esthetic differences: GitHub graph seems squeezed |  | ok
4 | 1478 | MVAghdis | 1478 | Ready | 1632 | ToDo | - | - | 2016-11-23 | ok |  | ok
4 | 1235 | MVAtdis | 1235 | Ready | 1637 | ToDo | - | - | 2016-11-23 | ok |  | ok
4 | 1481 | MVAlaplacedis | 1481 | Ready | 1635 | ToDo | - | Ready | 2016-11-23 | ok |  | ok
4 | 1264 | MVAcauchy | 1264 | Ready | 1626 | ToDo | - | . | 2016-11-23 | ok |  | ok
4 | 1492 | MVAmixture | 1492 | Ready | 1636 | ToDo | - | Ready | 2016-11-23 | ok |  | ok
4 | 1482 | MVAtdistail | 1482 | Ready | 1638 | ToDo | - | Ready | 2016-11-23 | esthetic differences: GitHub graph seems squeezed |  | ok
4 | 1479 | MVAghdistail | 1479 | Ready | 1633 | ToDo | - | - | 2016-11-23 | esthetic differences: GitHub graph seems squeezed |  | ok
4 | 1477 | MVAghadatail | 1477 | Ready | 1631 | ToDo | - | - | 2016-11-23 | ok |  | ok
4 | 1480 | MVAghsurface | 1480 | Ready | 1634 | ToDo | - | - | 2016-11-01 | ok |  | ok
4 | 1212 | MVAghcontour | 1212 | Ready | 1656 | ToDo | - | - | 2016-11-01 | ok |  | new graph: with labels
4 | 1230 | MVAsample1000 | 1230 | Ready | 1657 | ToDo | - | - | 2016-11-01 | it doesn't match Not all data points match |  | ok
4 | 1654 | MVAedfnormal | 1654 | Ready | 620 | ToDo | - | - | 2016-11-01 | graphs don't match |  | ok
4 | 1653 | MVAedfbootstrap | 1653 | Ready | 503 | ToDo | - | Ready | 2016-11-01 | it doesn't match |  | ok
5 | 1652 | MVAcondnorm | 1652 | Ready | 651 | ToDo | - | - | 2016-11-01 | esthetic differences: graph is rotated |  | Matlab code doesn't work!
7 | 2426 | MVAbluepullover | 2426 | Ready | 1651 | ToDo | - | - | 2016-11-01 | ok |  | The results don't coincide. It looks easy to be corrected.
7 | 1660 | MVAusenergy | 1660 | Ready | 1511 | ToDo | - | - | 2016-11-01 | ok |  | ok
7 | 1661 | MVAlrtest | 1661 | Ready | 1662 | ToDo |  | Ready | 2016-11-01 | ok |  | ok
7 | 1659 | MVAsimcidif | 1659 | Ready | 1658 | ToDo | - | - | 2016-11-01 | ok |  | ok
7 | 941 | MVAprofil | 941 | Ready | 455 | ToDo | - | Ready | 2016-11-01 | ok |  | ok
7 | 1684 | MVAsimcibh | 1684 | Ready | 311 | ToDo | - | - | 2016-11-01 | ok |  | ok
7 | 1682 | MVAlinreg2bh | 1682 | Ready | 425 | ToDo | - | Ready | 2016-11-01 | ok |  | ok
8 | 1683 | MVAresponsesurface | 1683 | Ready | 641 | ToDo | - | - | 2016-11-01 | esthetic differences: wider color spectrum in Book |  | ok
8 | 1532 | MVAcareffect | 1532 | Ready | 1678 | ToDo | - | - | 2016-11-01 | tables don't match |  | ok
8 | 2427 | MVAboshousing | 2427 | Ready | 1677 | ToDo | - | - | 2016-11-01 | ok |  | ok
8 | 1046 | MVAdrug | 1046 | Ready | 642 | ToDo | - | Ready | 2016-11-01 | one of the table doesn't match: Table 8.7 |  | ok
8 | 1716 | MVAdrug3waysTab | 1716 | Ready | - | - | - | - | 2016-10-28 | doesn't match : code doesn't run
8 | 2455 | MVAbankrupt | 2455 | Ready | 1676 | ToDo | - | - | 2016-10-28 | ok |  | ok
8 | 1679 | MVAdrugLogistic | 1679 | Ready | 1680 | ToDo | - | - | 2016-10-28 | ok |  | ok
9 | 2963 | MVAlassocontour | 2963 | Ready | - | - | - | - | 2016-10-28 | ok
9 | 2555 | MVAlassoregress | 2555 | Ready | - | - | - | - | 2016-10-28 | ok
9 | 2527 | MVAlassologit | 2527 | Ready | - | - | - | - | 2016-10-28 | ok
9 | 2525 | MVAgrouplasso | 2525 | Ready | - | - | - | - | 2016-10-28 | ok

## Chapters 10 to 20
Chapter | ID github | Name | R |  | Matlab |  | SAS
|  |  | ID old | transfered | ID old | transfered | ID old | transfered | Review Date | Git (R) vs Book | Git vs. Slides | Matlab Check (coincides with R Codes)
10 | 1114 | MVAdecofood | 1114 | Ready | 475 | ToDo | - | Ready | 01.09.2016 | signs of the data don't match |  | ok
11 | 1225 | MVApcasimu | 1225 | Ready | 1242 | ToDo | - | - | 01.09.2016 | ok |  | ok
11 | 945 | MVApcabank | 945 | Ready | 1670 | ToDo | - | Ready | 08.09.2016 | esthetic differences |  | ok
11 | 948 | MVApcabankr | 948 | Ready | 1671 | ToDo | - | Ready | 08.09.2016 | doesn't match |  | ok
11 | 1223 | MVApcabanki | 1223 | Ready | 653 | ToDo | - | Ready | 08.09.2016 | esthetic differences ¦ second graph |  | ok
11 | 2511 | MVAnpcafood | 2511 | Ready | 1669 | ToDo | - | Ready | 08.09.2016 | esthetic differences ¦ first graph |  | ok
11 | 1048 | MVAcpcaiv | 1048 | Ready | - | ToDo | - | - | 01.12.2016 | ok |  | ok, the output of the new codes (R and Matlab) corresponds to the figure 5 of the paper "The Dynamics of Implied Volatilities: A Common Principal Components Approach"
11 | 1118 | MVAnpcahousi | 1118 | Ready | 1239 | ToDo | - | Ready | 08.09.2016 | doesn't match |  | ok, changed R Code. The fourth plot is the same as the first, the it was ommited.
11 | 1117 | MVAnpcahous | 1117 | Ready | - | - | - | Ready | 08.09.2016 | esthetic differences |  | R code has an error in the line 29, the mean value makes no sense. Correct this when doing matlab code! This code is imilar to the previous one.
11 | 1215 | MVAnpcabank | 1215 | Ready | 654 | ToDo | - | Ready | 08.09.2016 | doesn't match |  | ok
11 | 1216 | MVAnpcabanki | 1216 | Ready | 408 | ToDo | - | Ready | 08.09.2016 | doesn't match: mirrored image |  | ok
11 | 1115 | MVAnpcausco | 1115 | Ready | 655 | ToDo | - | Ready | 08.09.2016 | ok |  | ok
11 | 1116 | MVAnpcausco2 | 1116 | Ready | 1674 | ToDo | - | Ready | 08.09.2016 | ok |  | ok
11 | 949 | MVAnpcausco2i | 949 | Ready | 1675 | ToDo | - | Ready | 08.09.2016 | esthetic differences ¦ first graph |  | ok
11 | 986 | MVAnpcatime | 986 | Ready | 1673 | ToDo | - | Ready | 08.09.2016 | esthetic differences ¦ both graphs |  | ok
12 | 2159 | MVAfactcarm | 2159 | Ready | 1398 | ToDo | - | Ready | 08.09.2016 | ok |  | Error in Matlab Code when calculating eigenvalues and vectors
12 | 1211 | MVAfacthous | 1211 | Ready | 1672 | ToDo | - | - | 08.09.2016 | doesn't match ¦ graph 4: mirrored image |  | ok. I suggest to change the name of the axes.
13 | 1201 | MVAclus8p | 1201 | Ready | 1664 | ToDo | - | Ready | 08.09.2016 | esthetic differences ¦ first graph |  | ok
13 | 1202 | MVAclusbank | 1202 | Ready | 1665 | ToDo | - | Ready | 08.09.2016 | graphs don't match |  | Matlab code doesn't produce the plot with the groups.
13 | 1205 | MVAclusfood | 1205 | Ready | 1667 | ToDo | - | Ready | 08.09.2016 | ok |  | Matlab code only produces the plot of the dendogram and omit the other two.
13 | 1204 | MVAclusbh | 1204 | Ready | 1666 | ToDo | - | Ready | 08.09.2016 | ok |  | ok
14 | 1209 | MVAdisnorm | 1209 | Ready | 1733 | ToDo | - | - | 08.09.2016 | doesn't match |  | ok, modified R code
14 | 2454 | MVAaper | 2454 | Ready | 656 | ToDo | - | Ready | 08.09.2016 | doesn't match: the names are not correctly assigned, compare tables of pages 409 and 417 |  | ok
14 | 928 | MVAdisfbank | 928 | Ready | 493 | ToDo | - | Ready | 08.09.2016 | ok |  | ok
14 | 1208 | MVAdiscbh | 1208 | Ready | 1692 | ToDo | - | Ready | 08.09.2016 | color differences, can't find table 14.1 |  | Matlab Code doesn't work
14 | 2344 | MVAaerbh | 2344 | Ready | 1701 | ToDo | - | - | 08.09.2016 | can't find table 14.2 |  | Matlab Code doesn't work
15 | 1072 | MVAcorrjourn | 1072 | Ready | 428 | ToDo | - | Ready | 08.09.2016 | esthetic differences |  | ok
15 | 1113 | MVAcorrbac | 1113 | Ready | 510 | ToDo | - | Ready | 08.09.2016 | don't match: mirrored graphs |  | ok
15 | 1073 | MVAcorrcrime | 1073 | Ready | 658 | ToDo | - | Ready | 08.09.2016 | esthetic differences |  | ok
16 | 2086 | MVAcancarm | 2086 | Ready | 2087 | ToDo | - | Ready | 08.09.2016 | doesn't match + (typo book) |  | ok, I changed the tittle of the plots from R and Matlab but not of the one from SAS
17 | 930 | MVAMDScity1 | 930 | Ready | 462 | ToDo | - | Ready | 09.09.2016 | esthetic differences |  | Matlab Code does not produced the expected plot
17 | 931 | MVAMDScity2 | 931 | Ready | 431 | ToDo | - | Ready | 09.09.2016 | esthetic differences |  | Matlab Code does not produced the expected plot
17 | 1214 | MVAmdscarm | 1214 | Ready | 1687 | ToDo | - | Ready | 09.09.2016 | graphs don't match |  | The plot of the correlations produced by the Matlab code does not correspond to the ones of R and SAS
17 | 933 | MVAMDSpooladj | 933 | Ready | 318 | ToDo | - | Ready | 09.09.2016 | esthetic differences |  | ok
17 | 932 | MVAMDSnonmstart | 932 | Ready | 659 | ToDo | - | Ready | 09.09.2016 | esthetic differences |  | Matlab Code does not produced the expected plot
17 | 934 | MVAnmdscar1 | 934 | Ready | 482 | ToDo | - | Ready | 09.09.2016 | ok |  | ok
17 | 935 | MVAnmdscar2 | 935 | Ready | 660 | ToDo | - | Ready | 09.09.2016 | esthetic differences |  | ok
17 | 936 | MVAnmdscar3 | 936 | Ready | 661 | ToDo | - | Ready | 09.09.2016 | esthetic differences |  | ok
18 | 757 | MVAcarrankings | 757 | Ready | 1685 | ToDo | - | - | 09.09.2016 | esthetic differences |  | ok
17 | 1686 | pava | - | - | 1686 | ToDo | - | - | 19.12.2016 | ok |  | ok, this is a matlab function used in the quantlet MVAcarrankings
19 | 1229 | MVAreturns | 1229 | Ready | 1689 | ToDo | - | - | 09.09.2016 | esthetic differences |  | ok
19 | 1227 | MVAportfol_IBM_Ford | 1227 | Ready | 1697 | ToDo | - | - | 09.09.2016 | esthetic differences, name in book: MVAportfolIBMFord
19 | 1226 | MVAportfol | 1226 | Ready | 1688 | ToDo | - | - | 09.09.2016 | esthetic differences
20 | 1268 | MVAsimdep1 | 1268 | Ready | - | - | - | - | 09.09.2016 | ok
20 | 2305 | MVAsimdepex | 2305 | Ready | - | - | - | - | 09.09.2016 | doesn't match
20 | 2154 | MVAppexample | 2154 | Ready | 2153 | ToDo | - | - | 09.09.2016 | ok
20 | 1234 | MVAsirdata | 1234 | Ready | 1703 | ToDo | - | - | 09.09.2016 | esthetic differences ¦ graph 1
20 | 1233 | MVAsir2data | 1233 | Ready | - | - | - | - | 09.09.2016 | esthetic differences
20 | 1964 | MVAsvmOrangePeel | 1964 | Ready | - | - | - | - | 09.09.2016 | doesn't match
20 | 1965 | MVAsvmSpiral | 1965 | Ready | - | - | - | - | 09.09.2016 | doesn't match
20 | 1966 | MVAsvmSig100C1 | 1966 | Ready | - | - | - | - | 09.09.2016 | ok
20 | 1967 | MVAsvmSig2C1 | 1967 | Ready | - | - | - | - | 09.09.2016 | ok
20 | 1968 | MVAsvmSig05C200 | 1968 | Ready | - | - | - | - | 09.09.2016 | ok
20 | 1707 | MVACARTBan1 | 1707 | Ready | 1711 | ToDo | - | - | 09.09.2016 | esthetic differences
20 | 1708 | MVACARTBan2 | 1708 | Ready | 1712 | ToDo | - | - | 09.09.2016 | esthetic differences
20 | 1581 | MVAbankruptcydis | 1581 | Ready | 1582 | ToDo | - | - | 09.09.2016 | esthetic differences, name in book: MVAbancrupcydis
20 | 1709 | MVACARTGiniTree1 | 1709 | Ready | 1713 | ToDo | - | - | 09.09.2016 | esthetic differences
20 | 1710 | MVACARTTwoingTree1 | 1710 | Ready | - | - | - | - | 09.09.2016 | esthetic differences
20 | 904 | MVAppsib | 904 | Ready | 1696 | ToDo | - | - | 09.09.2016 | can't find figure 20.35

## New Quantlets
Name | R | Matlab | SAS | Review Date
MVAspecclustspiral | ToDo | - | - | 2016-12-07